## Sheet1
Sl. No. | Modules | Impacted Area | Story Points | Assumption
1 | Common Code across CostShare | Changes are required in Entity ,Mapper ,Service layer ,DAO ,Junits and automation scripts . Which covers functionality of - Retriveing the plan on summary screen Add Occurences Delete Occurrence Add Scenario Copy Occurrence Save as Draft Submit with validation View Scenario Save Scenario and save as draft scenario Common Scenario across occurences Common occurences across multiple plan. Delete Scenario Cost Share period Changes. | 350 | UI estimation are standard considering no changes required in UI. No changes required in Scenario builder . Maximum and Variance functictionality is not clear. Any new functinality or logic improvement will be considered as new story.
2 | Copay | Changes required in Service , Mapper , DAO , Junits and Automation scripts . Changes related to Other occurences. Saves as Draft and Submit. | 175
3 | Coinsurance | Changes required in Service , Mapper , DAO , Junits and Automation scripts. Chnages related to network level changes related to General and Other occurences. | 150
4 | OPX | Changes required in Service , Mapper , DAO , Junits and Automation scripts . Relationship tier level changes Changes in Saves as draft and Submit. Changes in fetching the default plan. | 225